## Mix Analyzer Tracker
# | Category | Task | Status | Priority | Notes | Effort
CORE ANALYSIS (static, on file load)
1 | Analysis | K-weighted LUFS (BS.1770-4) | Done | Critical | Two-stage biquad, 400ms gating, abs+rel gate. Bug: short-term only measures final 3s — should track max across track. | Done
2 | Analysis | True Peak (4x Catmull-Rom) | Done | Critical | ~0.3-0.5dB variance vs ITU FIR spec. Acceptable for now. | Done
3 | Analysis | FFT spectrum + band distribution | Done | Critical | Verified Cooley-Tukey, Hann window, 48 averaged frames. 7-band energy distribution. Bug: no slope compensation (need configurable 0/3/4.5 dB/oct). | Done
4 | Analysis | Stereo correlation + multiband M/S | Done | High | Time-domain overall + FFT-domain per-band. Currently 7-band — need to add 3-band (L/M/H) grouping as primary view. | Done
5 | Analysis | Waveform + vectorscope + RMS/peak/crest/DR/clipping | Done | High | All working. Waveform is 1200-point mono. Vectorscope is 5000-point static Lissajous. | Done
6 | Analysis | BPM detection (onset + autocorrelation) | Done | High | Enhanced autocorrelation: hop=256, harmonic scoring (AC[lag]+0.5*AC[2lag]+...), octave correction fixed. Verified 144 BPM on test track. | Medium
7 | Analysis | Key detection (chromagram + Krumhansl profiles) | Done | High | Chromagram via FFT bin->pitch class + Krumhansl-Kessler Pearson correlation. Returns key/root/mode/confidence/chroma. | Medium
8 | Analysis | Spectral waveform data (per-frame band energies) | Done | Critical | During FFT analysis, extract per-frame energy in 3+ bands for spectral coloring. Same FFT data, just partition bins → color map per time-slice. Foundation for spectral waveform display. | Medium
PLAYBACK ENGINE
9 | Playback | Full-quality playback + play/stop/seek | Done | Critical | BufferSource → destination. disconnect-first pattern. Playhead on waveform. Click-to-seek. | Done
10 | Playback | Volume control (GainNode) | Done | High | GainNode in audio output chain. Volume slider 0-100% in transport bar. | Small
11 | Playback | Mono preview toggle | Done | High | ChannelMerger to sum L+R. MONO button in transport bar. Restarts playback to rebuild audio graph. | Small
12 | Playback | 3-band filter bank (live analysis path) | Done | Critical | LP 200Hz / BP 200-4kHz / HP 4kHz per channel = 6 AnalyserNodes. Wideband L/R added for vectorscope + M/S. | Done
13 | Playback | Band solo/mute (audio output) | Todo | Medium | Route filter bank to output via GainNodes. Solo = hear only that band. Advanced diagnostic tool. | Medium
14 | Playback | Playback speed / loop region | Todo | Low | BufferSource.playbackRate + loop/loopStart/loopEnd. | Small
LIVE VISUALIZATION (during playback)
15 | Live Viz | Live spectrum analyzer (Canvas) | Done | Critical | Line + spectrograph modes combined MiniMeters-style (spectrograph scrolls in BG, live curve on top). M/S toggle works in both modes. | Done
16 | Live Viz | 3-band stereo phase meter | Done | Critical | Pearson correlation per band + stereo width. Dot indicator maps -1..+1 to L..R axis. | Medium
17 | Live Viz | Live LUFS meter (momentary + short-term) | Done | Critical | Momentary (400ms RMS) + short-term (3s rolling avg) bars. Peak hold with slow decay. | Medium
18 | Live Viz | Live vectorscope (Canvas) | Done | Medium | Real-time M/S Lissajous from wideband L/R analysers. Multiband RGB coloring: red=Low, green=Mid, blue=High per sample. | Medium
19 | Live Viz | Spectrogram (scrolling time×freq heatmap) | Todo | Low | Canvas heatmap. Color = magnitude. Horizontal or vertical. Piano key overlay optional. | Large
WAVEFORM & DISPLAY
20 | Display | Spectral waveform (frequency-colored) | Done | Critical | Each time-slice colored by frequency content: red=low, green=mid, blue/purple=high. Vertical stack per column = band RMS amplitudes. Toggle between uniform/spectral modes. Uses data from task #8. | Large
21 | Display | BPM/key colored regions on waveform | Todo | High | Overlay detected BPM and key as colored sections. Different hue per key (chromatic mapping). BPM number per region. Contrasting borders at change points. | Medium
22 | Display | Chromagram visualization | Todo | Medium | 12-row heatmap of pitch class energy over time. Shows key changes, chord progressions, tonal density. | Medium
23 | Display | Band toggle switches (3-band: L/M/H) | Done | High | Three colored buttons controlling visibility across all multiband views. Click=toggle, Shift+click=solo. Compact bar in toolbar. | Small
24 | Display | Canvas migration for waveform | Done | Medium | setupCanvas() helper: DPR-aware scaling on all 5 draw functions. CSS height replaces HTML width/height attrs. | Done
EDM FEEDBACK ENGINE
25 | Feedback | Loudness / True Peak / DR / LRA feedback | Done | Critical | Genre-aware thresholds. FL Studio tips. | Done
26 | Feedback | Sub mono + stereo width + phase warnings | Done | Critical | Flags >10% sub width, negative correlation, excessive width. | Done
27 | Feedback | Spectral balance (mud/harshness/dullness) | Done | High | 200-300Hz mud zone, air harshness, sub excess. | Done
28 | Feedback | Genre target profiles (EDM + Hip-hop/Pop/Rock/Lo-fi) | Done | Medium | All 5 genres have distinct 30-point curves with per-genre colors and tolerance bands. Per-genre colors: EDM=pink, Hip-hop=orange, Pop=cyan, Rock=yellow, Lo-fi=green. | Small
29 | Feedback | Kick/bass separation + sidechain detection | Todo | Medium | Transient analysis to distinguish kick vs bass. Detect ducking patterns = sidechain present. | Medium
30 | Feedback | Spectrum slope compensation | Done | Medium | Adjustable 0/3/4.5 dB/oct slope to match Pro-Q/Span convention. | Small
31 | Feedback | Export feedback as report (PDF/MD) | Todo | Low | Generate downloadable summary of all findings. | Medium
UI / PREFERENCES
32 | UI | Preferences panel | Done | High | LUFS target, TP ceiling, mono crossover, vectorscope/band toggles. | Done
33 | UI | Three-view tabs + multi-stem + masking | Done | High | Analysis/Stereo/Feedback views. Stem tabs. Masking comparison. | Done
34 | UI | 3-band stereo as primary stereo view | Done | High | Replace 7-band as default. Keep 7-band as 'Advanced' toggle. | Small
35 | UI | Keyboard shortcuts | Todo | Medium | Space=play/pause, ←→=seek, M=mono, 1/2/3=views, L/M/H=band toggles. | Small
36 | UI | Drag-and-drop + file loading | Done | High | Working for all audio formats. | Done
37 | UI | Code de-minification | Done | Medium | Variables over-compressed (S.cd, S.dm etc). Expand for maintainability before major features. | Medium
REFERENCE & COMPARISON
38 | Reference | A/B reference comparison | Todo | High | Load reference track, level-match (LUFS-normalize), compare spectrum/LUFS/stereo/DR overlaid. Switch between tracks. Core mixing workflow. | Large
39 | Reference | Target curve overlay | Todo | High | Drag reference WAV → overlay its spectrum curve on yours. MiniMeters flagship feature. | Medium
40 | Reference | Reference library + profile generation | Todo | Medium | Local storage. Analyze references → average spectral/stereo/LUFS profiles per genre. SQLite metadata. | Large
41 | Reference | Download via yt-dlp / Cobalt | Todo | Medium | Python backend: yt-dlp for SoundCloud/YouTube. Cobalt requires self-hosted instance for programmatic use. Best quality audio. | Medium
NEURAL / AI (Python backend)
42 | Neural | Genre detection (CLAP embeddings) | Todo | High | Audio → CLAP vector → genre classifier. Fine-tuned on EDM subgenres. | Large
43 | Neural | Song similarity + discovery | Todo | Medium | Cosine similarity on CLAP vectors. YouTube Data API for finding similar tracks. | Large
44 | Neural | Stem separation (Demucs) | Todo | Medium | HTDemucs vocal/drum/bass/other. GPU-accelerated. Per-stem analysis. | Large
45 | Neural | LLM-powered mixing advice (Claude API) | Todo | Medium | Feed all analysis + reference comparison data → natural language recommendations. | Large
FLP INTEGRATION
46 | FLP | PyFLP parser (mixer routing, plugin chains) | Todo | Medium | Extract structure. Note: no FL21 support yet. | Medium
47 | FLP | Parametric EQ 2 binary parser | Todo | Medium | Binary structure documented. 7 bands × level/freq/bw/type/order. | Large
48 | FLP | Plugin chain analysis + recommendations | Todo | Low | Cross-reference plugin names with audio analysis. Flag missing HPF, etc. | Medium
INFRASTRUCTURE
49 | Infra | Python FastAPI local backend | Todo | High | Serves reference mgmt, neural engine, yt-dlp downloads. Localhost API. | Large
50 | Infra | Web Worker for heavy analysis | Todo | Medium | Offload FFT/LUFS/chromagram/BPM to worker. Prevents UI freeze on long files. | Medium
51 | Infra | Electron / Tauri desktop wrapper | Todo | Low | Standalone app. Local filesystem, GPU access, Python backend. | Large
52 | Infra | Persistent settings + project state | Todo | Medium | Save prefs, reference library, analysis history across sessions. | Medium
BUGS & TECH DEBT
53 | Bug | LUFS short-term: only final 3s window | Done | Medium | Fixed: reuses stBlocks from LRA loop, takes Math.max(...absGated). Was only measuring tail 3s window. | Small
54 | Bug | True Peak: Catmull-Rom vs ITU FIR | Todo | Low | ~0.3-0.5dB variance. Acceptable but imprecise. | Medium
55 | Bug | No error boundary / graceful degradation | Todo | Low | Corrupt files can crash the app. | Small
56 | Debt | SVG → Canvas waveform migration | Done | Medium | Resolved by Task #24 Canvas migration in Phase 2. | Done
IMPLEMENTATION PHASES (consolidated roadmap)
P1 | Phase | Spectral waveform + 3-band static stereo + genre re-add | Done | Critical | Rendering changes on existing data. Per-frame band energies from FFT → colored waveform. Regroup 7-band stereo → 3-band L/M/H primary view. Re-add genre targets. Tasks: #8, #20, #23, #28, #30, #34. | Medium
P2 | Phase | 3-band filter bank + live spectrum + Canvas migration | Done | Critical | Build BiquadFilter bank (task #12). Canvas-based live spectrum (task #15). Migrate waveform to Canvas (task #24). Foundation for ALL live viz. | Large
P3 | Phase | Live LUFS + 3-band stereo phase + playback controls | Done | Critical | Wire real-time K-weight LUFS (task #17). 3-band correlation display (task #16). Volume + mono toggle (tasks #10, #11). Makes playback genuinely useful. | Medium
P4 | Phase | BPM + Key detection with waveform overlay | Todo | High | Onset → BPM (task #6). Chromagram → Key (task #7). Windowed for changes. Colored regions + chromagram viz (tasks #21, #22). | Medium
P5 | Phase | Reference A/B + interactive EQ + band solo | Todo | High | Load reference, level-match, overlay (tasks #38, #39). Band solo/mute on output (task #13). EQ isolation via filter bank. | Large
P6 | Phase | Python backend + neural engine + desktop app | Todo | Medium | FastAPI + yt-dlp + CLAP + Demucs + Claude API. Electron/Tauri. Tasks: #41-#52. | Large
VERSION COMPARISON ENGINE
57 | VersionCmp | Version group management | Todo | High | UI to group multiple files as versions of the same track (drag into a 'version set' or name-based auto-grouping like 'track_v1.wav', 'track_v2.wav'). Each version gets analyzed independently using existing analysis pipeline (#1-8). Store results as array of analysis objects keyed by version label. OVERLAP: reuses existing multi-stem tab architecture (#33) — versions are conceptually the same as stems but with comparison logic instead of masking logic. | Small
58 | VersionCmp | Per-metric delta comparison | Todo | Critical | Core diffing engine. For each metric pair (LUFS, DR, crest, TP, stereo width, correlation, per-band energy), compute delta between all version pairs. Output: matrix of [metric × version-pair] with signed difference and magnitude. Example: 'v4 is 2.1 dB louder (LUFS) than v2' or 'v3 has 15% more sub energy than v6'. OVERLAP: reuses ALL existing analysis data from #1-8 — no new DSP needed, purely comparison logic on stored results. | Medium
59 | VersionCmp | Time-aligned sectional comparison | Todo | High | Split each version into sections (intro/verse/drop/breakdown/outro) using onset/energy segmentation or fixed-length windows. Compare metrics PER SECTION across versions. Enables: 'the drop in v4 has better dynamics than v6 but the breakdown in v6 has cleaner highs'. OVERLAP: builds on BPM/beat detection (#6) for intelligent segmentation. Also shares windowed analysis approach with key/BPM change detection (#7). | Large
60 | VersionCmp | Best-of-each recommendation engine | Todo | Critical | For each metric category (loudness, dynamics, spectral balance, stereo, transients, clarity), identify which version scores 'best' based on configurable criteria (e.g., 'best dynamics' = highest crest factor + LRA; 'best spectral' = flattest deviation from genre target). Output natural language: 'Dynamics: v4 (crest 8.2dB, LRA 6.1LU) > v6 (crest 5.1dB, LRA 3.8LU)'. Configurable: what 'best' means per category. OVERLAP: uses genre targets from feedback engine (#28) as the scoring reference. | Medium
61 | VersionCmp | Spectral difference heatmap | Todo | Medium | Visual display of frequency-domain differences between two selected versions. X=frequency (log), Y=dB difference (positive=version A louder, negative=version B louder). Colored heatmap showing where versions diverge spectrally. Like FabFilter Pro-Q's EQ Match difference curve but for comparison, not correction. OVERLAP: uses same averaged FFT spectrum data from #3. Extends existing Spec component. | Medium
62 | VersionCmp | Per-element detection (kick/snare/perc clarity) | Todo | High | REQUIRES STEM SEPARATION (Demucs, task #44) or transient-based element isolation. Approach 1 (no stems): detect kick hits via low-frequency transient peaks, measure per-hit spectral profile and peak level across versions. Detect snare via mid-frequency transients. Compare clarity = spectral contrast in each element's frequency range. Approach 2 (with stems): run Demucs on each version → analyze drum stem, bass stem independently → compare. Approach 1 is feasible in-browser; Approach 2 requires Python backend. ROADBLOCK: in-browser transient isolation is approximate — works for obvious kicks/snares but unreliable for complex arrangements. | Large
63 | VersionCmp | Anomaly detection (extraneous elements) | Todo | Medium | Identify spectral anomalies: narrow-band peaks that are significantly louder than surrounding frequencies (resonances), broadband energy that appears in one version but not others (extraneous elements), sudden amplitude spikes not aligned with beats (artifacts/clicks). Algorithm: compute per-frame spectral deviation from the cross-version average spectrum. Frames/bins that exceed threshold = anomalies. Flag with time position and frequency. OVERLAP: extends spectral analysis from #3 and masking detection concept from existing masking view. | Large
64 | VersionCmp | A/B playback switcher | Todo | High | During playback, switch between versions at same time position. Level-matched (LUFS-normalized). Instant switching with no gap. Uses existing playback engine (#9) with multiple BufferSources sharing a time reference. OVERLAP: directly extends Reference A/B (#38) — same switching mechanism, just applied to versions instead of external references. | Medium
65 | VersionCmp | Version comparison summary view | Todo | High | Dashboard showing all versions side-by-side: metric cards per version, winner badges per category, spectral difference overlay, timeline of per-section winners. Exportable as report. OVERLAP: extends existing feedback view (#25-27) and metric cards — same components, arranged in comparison layout. | Medium
UPDATED PHASE ROADMAP (with version comparison)
P1 | Phase | Spectral waveform + 3-band stereo + genre re-add | Done | Critical | Tasks: #8, #20, #23, #28, #30, #34. Rendering-only changes on existing data. | Medium
P2 | Phase | 3-band filter bank + live spectrum + Canvas waveform | Done | Critical | Tasks: #12, #15, #24. BiquadFilter bank infrastructure. Canvas migration. Foundation for all live viz. | Large
P3 | Phase | Live LUFS + 3-band stereo phase + playback controls | Done | Critical | Tasks: #10, #11, #16, #17. Volume, mono, live meters. Makes playback useful. | Medium
P4 | Phase | BPM + Key detection + waveform overlay | Todo | High | Tasks: #6, #7, #21, #22. Onset→BPM, chromagram→key. Colored regions. Chromagram viz. | Medium
P5 | Phase | Version comparison engine (base architecture) | Todo | High | Tasks: #57, #58, #60, #64, #65. Version grouping, per-metric deltas, best-of recommendations, A/B switcher, summary view. All build on existing analysis — no new DSP. Sectional comparison (#59) added once BPM detection from P4 is available. | Large
P6 | Phase | Reference A/B + interactive EQ + band solo | Todo | High | Tasks: #13, #38, #39. Reference overlay, EQ isolation, band solo/mute. Version A/B switcher (#64) shares code with reference A/B. | Large
P7 | Phase | Per-element detection + anomaly detection + Python backend | Todo | Medium | Tasks: #41-#45, #49, #59, #62, #63. Demucs stems enable per-instrument comparison. Anomaly detection. yt-dlp downloads. CLAP genre detection. LLM feedback. | Large
P8 | Phase | FLP integration + desktop app | Todo | Low | Tasks: #46-#48, #50-#52. PyFLP parser, EQ2 binary parser, Electron/Tauri wrapper. | Large
INTELLIGENT FEEDBACK SYSTEM (3-tier)
66 | Feedback AI | Tier 1: Dynamic template engine (offline, in-browser) | Todo | Critical | REPLACES current hardcoded feedback. Architecture: analysis data → rule engine (decision tree) → template selector → slot interpolation → natural language output. Rules evaluate COMBINATIONS of metrics, not single thresholds. Example rule: IF crest<5 AND lufs>-8 AND dr<4 THEN template='limiter_overwork' with slots filled from actual values. Template library organized by category (loudness, dynamics, spectral, stereo, transients, kick/bass). Each template has 3-5 variations to avoid repetitive phrasing. Training source: encode knowledge from mixing guides, Pensado, Scheps, iZotope guides, MasteringTheMix blog into ~200 rule+template pairs. ALWAYS AVAILABLE — no API needed. OVERLAP: replaces current edmFB() function entirely. Uses same analysis data from #1-8. | Large
67 | Feedback AI | Multi-factor correlation rules | Todo | High | The intelligence layer for Tier 1. Rules that cross-reference multiple metrics to give non-obvious advice. Examples: [high sub energy + low sub stereo width + low correlation = phase cancellation in bass layers, not a width problem], [high LUFS + low crest + moderate DR = clipper is doing the work well but limiter ceiling too aggressive], [mud zone heavy + kick in sub range + bass in low-mid = kick and bass are frequency-swapped from convention, consider swapping their EQ roles]. Each rule has: conditions (metric thresholds), confidence score, category, template ID, and a 'severity' that determines display priority. ~50-100 rules covers most common EDM mixing issues. | Medium
68 | Feedback AI | Template variation + phrasing engine | Todo | Medium | Avoid canned-sounding output. Each template has multiple phrasings that get randomly selected. Contextual connectors between findings ('additionally', 'this compounds the issue because', 'on the positive side'). Severity-based ordering — most impactful issue first. Summary opener that characterizes the overall mix ('this mix is loud but dynamically flat' vs 'solid fundamentals with some spectral issues'). All deterministic, no AI needed. | Medium
69 | Feedback AI | Tier 2: Local LLM integration (optional, offline) | Todo | Low | For users who want fully generative feedback without cloud dependency. Architecture: analysis JSON → structured prompt → local model (Llama 3 8B Q4, Phi-3, or Mistral 7B via llama.cpp or Ollama) → validation layer → output. Validation layer cross-checks LLM claims against actual data (reject if LLM says 'your LUFS is -14' when data shows -8). Requires ~4GB VRAM — your 4070 Ti handles easily. Training: fine-tune on mixing advice corpus (forum posts, tutorials, mixing textbook excerpts) or use RAG with a mixing knowledge base. ROADBLOCK: hallucination risk — LLM might recommend actions that contradict the data. Validation layer is critical. Lowest priority since Tier 1+3 cover most needs. | Large
70 | Feedback AI | Tier 3: Claude API deep analysis (cloud, highest quality) | Todo | High | Architecture: analysis JSON + version comparison data + reference comparison data → structured system prompt (mixing engineering principles, EDM conventions, FL Studio workflow context) → Claude API (claude-sonnet-4-20250514) → natural language feedback. System prompt encodes: mixing priorities (balance→EQ→dynamics→stereo→FX), genre conventions, common beginner mistakes, FL Studio-specific workflow tips. The analysis data gives Claude ground truth — it can't hallucinate about YOUR numbers because they're in the prompt. Cost: ~$0.003-0.01 per analysis (2-4k input tokens, 500-1k output). API key stored in prefs, optional. OVERLAP: replaces task #45 (LLM mixing advice) — same concept, now with structured tier system. | Medium
71 | Feedback AI | Mixing knowledge base (shared across tiers) | Todo | High | Structured knowledge base used by all 3 tiers. Categories: loudness (streaming targets, genre norms, gain staging), dynamics (compression types, limiter vs clipper, parallel processing), spectral (EQ conventions, frequency ranges per instrument, mud/harshness/dullness), stereo (mono below X Hz, M/S processing, width per element), transients (attack/release, crest factor, punch), kick/bass (sidechain, frequency separation, phase alignment), mastering (LUFS targets, TP ceiling, dithering). Format: JSON with rule conditions, explanations, FL Studio-specific tips, and severity weights. This is the 'brain' that Tier 1 executes directly, Tier 2 uses as RAG context, and Tier 3 includes in the system prompt. Source material: Mixing Secrets for the Small Studio (Senior), Mastering Audio (Katz), iZotope guides, MasteringTheMix blog, Sound On Sound articles. | Large
72 | Feedback AI | Version-aware feedback generation | Todo | Medium | Extension of all tiers to handle version comparison context. Instead of 'your crest factor is low', generates 'v4 recovered 3.1dB of crest factor compared to v2 — the transient preservation is notably better, likely from switching to a clipper-first chain. However, v4 lost 2dB of integrated LUFS, suggesting the clipper isn't fully compensating. Try raising the clipper ceiling by ~1dB.' Requires version comparison data from #58 (per-metric deltas) and #60 (best-of scoring). For Tier 3: Claude receives the full delta matrix and generates cross-version narrative. | Medium
73 | Feedback AI | Feedback API abstraction layer | Todo | High | Single function interface: generateFeedback(analysisData, options) → feedback[]. Options include: tier (1/2/3), detail level (brief/detailed/verbose), genre, version comparison data, reference comparison data. Tier 1 executes synchronously in-browser. Tier 2 calls local Ollama endpoint. Tier 3 calls Claude API. The UI doesn't care which tier generated the feedback — same component renders all of them. Fallback chain: try Tier 3 → if no API key or offline, fall to Tier 2 → if no local model, fall to Tier 1. OVERLAP: this replaces the current edmFB() call site. All feedback consumers (main feedback view, version comparison, reference comparison) call this single API. | Medium
71 | Live Viz | Spectrogram heatmap mode for live spectrum | Done | Medium | Toggle between line and heatmap modes. Scrolling spectrogram with frequency-colored heatmap (black→blue→cyan→yellow→white). ImageData pixel buffer with 2px scroll per frame. | Done
72 | Live Viz | Live spectrum curve smoothing + bass resolution | Done | Medium | FFT 4096 (was 2048) for better bass. 1/6 octave averaging instead of max-bin. Quadratic bezier curve interpolation for smooth lines. 400 points (was W pixels). | Done
73 | Display | Static spectrum improvements (scale, grid, genre colors) | Done | Medium | H 220 (was 180). Tighter auto-range (36dB min span, 3dB padding). Higher contrast grid lines. Per-genre colors (EDM=pink, Hip-hop=orange, Pop=cyan, Rock=yellow, Lo-fi=green). Genre name in spectrum header. | Done
74 | Live Viz | M/S mode for live spectrum | Todo | Medium | Toggle to display Mid (sum) and Side (difference) channels separately on the live spectrum canvas. Mid = (L+R)/2, Side = (L-R)/2 derived from AnalyserNode data per frame. Two overlaid curves or switchable: Mid in current color, Side in contrasting color (e.g. orange). Useful for checking mono compatibility and side channel energy distribution. | Small
75 | Analysis | M/S mode for static spectrum | Todo | Medium | Add Mid/Side view to the static post-analysis spectrum (SpectrumDisplay). Requires storing separate M and S FFT curves during computeSpectrum(). Toggle button alongside existing controls. Mid = mono sum, Side = stereo difference. Helps identify frequency ranges where the mix is wide vs mono. Pairs with the existing stereo correlation data. | Small
76 | Infrastructure | GitHub Actions cross-platform build (Win + Mac) | Done | Medium | build.yml: push tag v* triggers windows-latest (.exe NSIS+portable) + macos-latest (.dmg universal). Artifacts uploaded. | Done
77 | Infrastructure | Electron desktop app wrapper | Done | Medium | electron/main.cjs (CJS, renamed from .js to fix type:module conflict). electron-builder: NSIS installer + portable .exe. release/ gitignored. | Done
78 | Display | Waveform zoom + scroll | Done | Medium | 1x/2x/4x/8x zoom buttons + mouse wheel. Scroll slider. Auto-follows playhead when zoomed. Mini-map strip at waveform bottom. Seek accounts for zoom window. | Done
79 | Bugs | Verify BPM accuracy across multiple tracks | Todo | High | Tested on one track (144 BPM confirmed). Need 4-5 more tracks at varied tempos (90, 120, 170+ BPM) to validate enhanced AC algorithm. | Medium
80 | Bugs | PR creation blocked: orphan branch history | Todo | High | main and feature branch created as unrelated orphans. GitHub rejects PR. Fix: rebase feature commits onto proper main scaffold before opening PR. Repo: github.com/rossxo-m/MixAnalyzer | Small
81 | Infrastructure | App icon (icon.ico + icon.icns) | Todo | Low | electron-builder uses default Electron icon. Need 256x256 .ico (Windows) and 512x512 .icns (macOS). Can generate from single 1024x1024 PNG. | Small
82 | Bugs | Vectorscope multiband band/wideband fftSize mismatch | Todo | Medium | Band analysers fftSize=512, wideband fftSize=4096. Stride mapping (Math.round(bufSize/bandBufSize)) used but needs visual QA — coloring may be slightly misaligned at transients. | Small
74 | Live Viz | M/S mode for live spectrum | Done | Medium | M/S is a toggle button (not a mode). Works alongside line and spectrograph modes. lFreq/rFreq -> M=(L+R)/2, S=(R-L)/2 in dB domain. Mid=blue, Side=orange. | Done
75 | Analysis | M/S mode for static spectrum | Done | Medium | computeSpectrum returns spectrumPointsS (Side channel FFT). SpectrumDisplay has M/S toggle. Slope compensation applied to both M and S curves. | Done